## Introduction
This example Intervention Guide has been produced by the Donor Committee for Enterprise Development (DCED). It is designed to provide ideas and guidance for programmes implementing the DCED Standard for Results Measurement. It is an example only. It is based on a fictional case. Country information and statistics are also often fictitious. Resemblance to any specific programme is accidental. There is an ongoing discussion about the best way in which to structure a results measurement plan. It should be tailored to your organisation's needs. If you use this in your project, please tell us and give feedback at admin@enterprise-development.org
7th November 2019

## Summary
Intervention Summary
Intervention title: | Assisting Baggajute to expand production and enter export market
Programmatic area: | Sustainable production
Intervention manager: |  |  | Budget:
Intervention start Date: | MM-YYYY |  | Intervention end date: |  |  | MM-YYYY
Monitoring start Date | MM-YYYY |  | Monitoring end date: |  |  | MM-YYYY
Summary Impact
This summarises the project impact. It should be taken from the calculation sheet. You should change the common impact indicators or add more depending on what the project's impact indicators are. Figures can be disaggregated according to gender if it is relevant. If project does not make projections, it can summarise actual results. |  |  |  | Actuals |  |  | Projected
|  |  |  | Year 1 | Year 2 | Year 3 | Year 1 | Year 2 | Year 3
Total outreach
Additional income generated
Additional FTEs created
What is the problem that this intervention is trying to address? | Bangladesh is one of the largest producers and exporters of raw jute, a natural fibre used for cloth production. In 2016/17, the country earned US$563.9 million by exporting jute and jute goods. There is a huge demand for jute products, but the country is failing to exploit this export potential because companies are lagging behind in production and diversification of jute and jute products. Importing countries are increasingly becoming conscious about the benefits of natural yarns and are showing interest in jute products, especially as Bangladeshi jute products have a tight and soft weave. There are about 200 private jute mills in the country. However these jute mills do not use modern machines and lack the vision of how to tap into the export market.
Who is this intervention working with to address these constraints, and what is their incentive to cooperate? | Eco Market Development (EMD) programme partnered with one of the oldest and established jute mills in Bangladesh, which had recently expanded their business to make jute bags under the brand of Baggajute. Their main business is exporting jute yarn. In 2015 they started producing jute bags targeted at the local market. They have 20 stitching mahines and 200 workers making 30,000 basic jute bags. They would like to make more diversified and better quality bags to target the export market but it was considered a risky venture as it was new.
How will this intervention work with these actors to address the problem discussed above? | EMD and Baggajute's initial market research showed that there was increasing demand for high quality jute bags in Northern European markets. EMD designed an intervention with Baggajute to share the cost of five stitching machines which would help them increase the quality of jute bags. EMD would help to organise a training on how to operate these machines. Baggajute would hire 150 new workers to operate these machines, who will also receive training in higher quality bag production. EMD will support Baggajute to take part in an export fair so that they can market their products amongst international buyers. Baggajute will also need to source more raw jute from farmers. Baggajute offers a higher rate than market price to their farmers to ensure they get quality jute from supplying farmers.
Would the intervention create any displacement? Explain why or why not. | No. Jute is a growing international market, and there is a high demand for additional products.
Please describe how this intervention might separately affect men and women, including both positive and negative results? | Most workers working in Baggajute's jute bag production are women, as traditionally women have been taking a more active role in this sector with their background in weaving. Baggajute wants to hire female workers to work in this new production line as they feel they have had a good experience with female workers. EMD wants to follow up with these women to see if receiving training on finer techniques can help them earn a higher income than before.
Key assumptions underlying this intervention | Continuing growth in international jute market and prices. Ability of jute farmers to meet quality requirements of Baggajute Capacity of Baggajute to produce higher quality products
Record of Changes made to Measurement Plan
What change was made |  |  |  | Projected Year 2: Date of Change

## Results chain
Outputs
Activities
Outcomes
Impact
Baggajute procures 5 stitching machines
(March-April)
EMD signs partnership with Baggajute
(February)
Baggajute hires 150 female workers to operate the new machines
(April-May)
Baggajute hires two marketing managers to market new products for potential export markets
(April)
EMD trains female staff
(June)
Marketing managers attend export fair in Germany and interact potential clients
(May)
Stitching machine is installed and stitching lines are operational
(June)
Marketing managers start reaching out to potential European importers of high quality jute bags
(May-June)
Baggajute has capacity to produce high quality jute bags
(June)
Baggajute obtains export orders of high quality Jute bags
(July)
Baggajute produces high quality jute bags
(July onwards)
Baggajute sell high quality jute bags and earns profit
(July onwards)
Additional employment created for female workers who now work at Baggajute
Additional income created for jute farmers and Baggajute female workers
Other jute manufacturers make diversified products to enter the export market
Baggajute sources additional raw jute from jute farmers at a higher price (July onwards)
Female staff are skilled on how to operate new machines (June)

## RM Plan
Indicators and measurement
BOX FROM RESULTS CHAIN (Copy each step in the results chain) | QUANTITATIVE INDICATORS OF CHANGE | QUALITATIVE DATA COLLECTION NEEDS | HOW TO MEASURE | WHEN
EMD signs partnership with Baggajute (Feb) | Partnership contract |  | Observation | February
Baggajute procures 5 stitching machines (March -April)) | Stitching machines procured |  | Observation | April
Baggajute hires 150 female workers to operate the new machines (April - May) | Number of female workers hired | Reason for hiring female worker | Observation, Phone call with Baggajute | May
EMD organizes three week training for hired female staff (June) | Number of female workers who receive training | What was taught in training? Were the female workers comfortable with trainer? | In-depth interview with female workers | June
Baggajute hires 2 marketing managers to market new products in potential export markets (April) | Number of marketing managers hired | Job functions | Phone call with Baggitude | May
Marketing managers attend export fair in Germany (May) |  | Networking opportunities in job fare | Phone call with Baggitude marketing managers | June
Stitching machine is installed and stitching lines are operational (June) |  | Are stitching machines installed and ready to operate? | Phone call with Baggitude | July
Marketing managers start reaching out to potential European importers of high quality jute bags (May-June) | Number of exporters contacted | How the exporters were targetted | Phone call with Baggitude marketing managers | July
Baggajute has capacity to produce high quality jute bags (June) | Number of high quality jute bags that can be produced using new machines |  | Phone call with Baggitude | July
Jute bag importers place order for high quality jute bags (July) | Number of orders received Volume of order | Types of order received | In-depth interview with Baggitude | Interviews conducted with Baggijute and labourers every year to gauge progress
Baggajute produces high quality jute bags (July - June ) | Number of bags produced each year
Baggajute sell high quality jute bags and earns profit (July-June ) | Additional revenue and profit from selling quality jute bags | If no profit, why not
Additional employment created | Total additional labour (FTES) hired to make quality jute bags
Baggajute sources additional raw jute from jute farmers at a higher price (July onwards) | Amount of raw jute sourced from farmers
Number of farmers selling jute to Baggajute
Additonal price compared to alternative sources
Additional income created for jute farmers and Baggajute female workers | Net additional income received by farmers | Why did they increase their income? How has income been used in the household? | Survey with farmers and indepth interviews
| Net additional income received by labourers | Have female workers been able to use income in their households? Has there been a change in decision making power because of this work? | In-depth interview with female workers
Other jute manufacturers make diversified products to enter the export market | Number of additional jute manufacturers who enter the same market seeing Baggijute's profits | What motivated them to enter business | Stakeholder opinion | Based on market intel, follow-up will be established
Attribution plan
Actor | Method for assessing attribution
Baggijute | Before and after comparison with opinion
Laborers | Before and after comparison with opinion
Farmers | Difference in difference study, comparing price of jute sold to Baggajute with alternative market price of jute available to farmers

## Measurements and Calculations
Measurement and Calculations
INDICATORS (If more than one indicator per result chain box, place each indicator on a separate line.) | BASELINE (insert baseline data or information if it has been collected for the indicators) | PROJECTED |  |  | CALCULATION (In this column where relevant explain how calculations have been made including assumptions made) | ACTUALS |  |  | SOURCE OF EVIDENCE (Link to location of evidence or name of relevant documentation fromwhich findings have been taken)
|  | Year 1 | Year 2 | Year 3 |  | Year 1 | Year 2 | Year 3
Stitching machines procured |  | 5 | 5 | 5 | 5 machines will be procured
Number of female workers hired |  | 150 |  |  | 150 female workers will be hired in the first year.
Number of female workers who receive training |  | 150 |  |  | In the first year all 150 female workers will receive training.
Number of marketing managers hired |  | 2 |  |  | 2 marketing managers will be hired in the first year.
Number of exporters contacted |  | 10 | 15 | 20 | It is assumed that in the first year Baggajute makes contact with ten exporters and by year 2 and year 3, 5 additional exporters each year.
Number of orders received |  |  |  |  | It is not possible to yet make a good estimation on number of orders received. Hence calculations are made below on the basis of how much Baggajute thinks it can produce.
Total number of jute bags produced per year |  | 300000 | 400000 | 500000 | The full capacity of the machines is to produce a total of 800,000 bags annually. It is expected that because this is still a new market for Baggijute, they will secure orders to make 300,000 bags in Year 1 and it will increase by an additional 100,000 every subsequent year.
Jute fabric required per bag in kg |  | 0.65 | 0.65 | 0.65 | This is a rough estimation made by Bagijute's design team. Actuals will be adjusted
Total amount of jute fabric required every year (kg) |  | 195000 | 260000 | 325000
Total amount of raw jute required to produce jute fabric (bales) |  | 1113.45 | 1484.6 | 1855.75 | In order to make 1 ton (1000 kg) of jute fabric, 5.71 bales of raw jute is required.
Total area of land required to produce raw jute in acre |  | 172.7067 | 230.2755 | 287.8444 | Average production of jute is 1096 kg/acre. 1 bale = 170 kg
Total number of farmers producing raw jute |  | 345.4133 | 460.5511 | 575.6889 | An average farmer produces jute in 0.5 acre land.
Additional price offered by Baggijute per kg of jute in BDT |  | 15 | 15 | 15 | Market price for jute is BDT 40, Baggijute pays BDT 55 for farmers who produce better quality jute depending on colour and thickness.
Total additional profit earned by farmer in BDT |  | 2839297.5 | 3785730 | 4732162.5 | Production of jute requires minimal costs, so it is assumed that no additional cost will be incurred.
Total additional profit earned by each farmer in BDT |  | 8220 | 8220 | 8220
Total additional profit earned by each farmer in USD |  | 102.75 | 102.75 | 102.75 | 1 USD = 80 BDT
Total additional income earned by all farmers in USD |  | 35491.2188 | 47321.625 | 59152.0312
Total additional labour (FTES) hired to make quality jute bags |  | 150
Total additional income earned by each labourer in BDT per year |  | 72000 | 72000 | 72000 | The labourers are paid a salary of BDT 6,000 per month
Total additional income earned by each labourer in USD per year |  | 900 | 900 | 900 | 1 USD = 80 BDT
Total additional income earned by all labourers in USD per year |  | 135000 | 135000 | 135000
Net additional income received by all farmers and labourers in USD |  | 170491.2188 | 182321.625 | 194152.0312

## Lists (hidden)
Progress | Maturity | Likelihood | Drivers | Driverstatus | HML | Challenges | YN | Department | Additionality | BBB | Sustainability | Onetoten | Relevance | RAG
On ice / cancelled | Catalising ideas | 0-10% | Increase productivity of a business unit (leading to increased profitability) | It is still a driver that we hope to achieve | High | Need to access appropriate external financing to enable further development of the project | Yes | Social responsibility / public affairs / community relations | Without BIF support the business model would not have progressed at all | The innovative idea is better designed | The progress of the business model would not be majorly affected | 1 | High | Red
On hold / stalled | Concept development | 20% | Decrease costs of a business unit (leading to increased profitability) | Some initial gains on this driver are now being realised | Medium | Need to access further internal resourcing and/or financing to enable further development of the project | No | Operations / Procurement / Supply / Sales | Due to BIF support, the innovative idea is better designed, or proceeding more quickly, or bigger than it would have been | The innovative business model is proceeding more quickly | Implementation of the business model will still carry on, but at a slower pace | 2 | Medium | Amber
Progressing lower than expected | Scoping / design | 30% | Establish ‘first mover advantage’ by deveoping a new competitive advantage / differentiation from competitors | Yes, the project is already delivering this driver | Low | Low projected financial return on investment in the project – not seen to be commercially viable |  | Central innovation / Strategy / R&D | BIF support was useful to us and made it easier to progress, although it has not resulted in specific identifiable change compared to what would have happened | The innovative business model is bigger than it would have been | BIF support is crucial to the next phase of implementation of the business model. It is uncertain what would happen if BIF support was interrupted | 3 | Low | Green
Progressing in line with expectations | Seeking resource for pilot | 40% | Increase market share of your current product / business market | We no longer think this is a core driver for the project |  | Lack of identified social or development impacts |  | General management | BIF support made no difference |  | The implementation of the business model would certainly stall | 4 | Not relevant
Progressing faster than expected | Piloting | 50% | Access or create new markets for your current product / business (e.g. geographic markets, demographic markets, product markets (e.g. Fair Trade / Organic / other certification) etc |  |  | Projected break-even point is too far in the future / will take too long to reap returns |  | Other | BIF support had net negative results |  |  | 5
| Seeking resource for implementation | 60% | Increase/ guarantee security and sustainability of your supply chain |  |  | High risk project | [5 empty] | 6
| Fully implemented | 70% | Enhance brand identity / value, customer appeal |  |  | Insufficient internal senior buy in &/or concensus (please explain why) | [5 empty] | 7
| Scaling up | 80% | Lower reputational risk |  |  | Lack of market information means difficult to assess potential return on investment | [5 empty] | 8
|  | 90% |  |  |  | Lack of information about similar work elsewhere | [5 empty] | 9
|  | 100% |  |  |  | Lack of appropriate skills within the company to further develop the project (knowledge, awareness, expertise) | [5 empty] | 10
|  | Already reached |  |  |  | Need new &/or different partnerships with government
Need new &/or different partnerships with others
Not sure how to move from pilot to scale up
Policy and regulatory environment are restrictive (please explain which are the restrictions)
Insufficient relevant national infrastructure (e.g. roads / power supply)
Insufficient relevant company infrastructure (e.g. offices, shops or factories)
Lack of demand &/or lack of marketing or market creation expertise